## PREP
ASSET |  | CONCEPT | MODEL SHEET | MODELING | SET-UP 2D | SHADING | LIGHTING | History
CH | assetID | TO DO | TO DO | NONE | TO DO | NONE | NONE | Escaleta | TO DO
ST | assetID | TO DO | TO DO | TO DO | NONE | TO DO | TO DO | Guión | TO DO
[8 empty] | StoryTelling | TO DO
[8 empty] | StoryBoard | TO DO
[8 empty] | ColorScript | TO DO

## PROD
SEQUENCE | SHOT | CAM |  | ASSETS | 2D ANIMATIC | LAYOUT 2D | ANIMATION | FX | CLEAN UP | COLOR | LIGHTING | COMPO | LEVEL
sq01 | sh001 | PM | Trav. In | ch_assetID/pr_assetID/st_assetID | TO DO | TO DO | TO DO | TO DO | TO DO | TO DO | TO DO | TO DO | Easy
sq01 | sh002 | PM | Trav. Out | ch_assetID/pr_assetID/st_assetID | NONE | TO DO | IN PROGRESS | DONE | PAUSE | TO DO | TO DO | TO DO | Mid
sq01 | sh003 | PM | Trav. Circ | ch_assetID/pr_assetID/st_assetID | TO DO | TO DO | TO DO | TO DO | TO DO | TO DO | TO DO | TO DO | Hard
sq01 | sh004 | PM | Pan. Vert | ch_assetID/pr_assetID/st_assetID | TO DO | TO DO | TO DO | TO DO | TO DO | TO DO | TO DO | TO DO | Hard
sq02 | sh005 | PM | Pan. Hor | ch_assetID/pr_assetID/st_assetID | TO DO | TO DO | TO DO | TO DO | TO DO | TO DO | TO DO | TO DO | Hard
sq02 | sh006 | PM | None | ch_assetID/pr_assetID/st_assetID | TO DO | TO DO | TO DO | TO DO | TO DO | TO DO | TO DO | TO DO | Hard

## RRSS
Septiembre | Octubre | Noviembre | Diciembre | Enero | Febrero | Marzo | Abril | Mayo | Junio | Julio | Agosto | Septiembre

## SCHEDULE
| Septiembre | Octubre | Noviembre | Diciembre | Enero | Febrero | Marzo | Abril | Mayo | Junio | Julio | Agosto | Septiembre
DEV
Escaleta
Guión
StoryTelling
StoryBoard
Concept Art
Voices
PREP
Model sheet
Set-up
Color Script
CharFX
PROD
Layout
Animation
FX
Clean-up
Color
Lighting
Compositing
SoundFX
Infographic
TFG
Dossier
Attach
Presentation
Reel

## NOTES
TASK | ASSET TYPE | CAMERA |  | MOV. CAM. | LEVEL
NONE | CH | PPP | Primerisimo Primer Plano | Trav. In | Easy
TO DO | PR | PP | Primer Plano | Trav. Out | Mid
IN PROGRESS | ST | PM | Plano medio | Trav. Circ | Hard
DONE | CM | PA | Plano americano | Pan. Vert
PAUSE | LB | PG | Plano general | Pan. Hor
|  | GPG | Gran Plano General | Steady
None